## Sheet1
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 4.25 | 5 | 5.75 | x
B | Develop marketing strategy |  | 6.8 | 8 | 9.2 | x
C | Design brochure | A | 5.1 | 6 | 6.9 | x
D | Develop product prototype |  | 0
D1 | Requirements analysis | A | 6.8 | 8 | 9.2 | x |  |  | x | x
D2 | Software design | D1 | 6.8 | 8 | 9.2 | x | x
D3 | System design | D1 | 6.8 | 8 | 9.2 |  |  | x
D4 | Coding | D2, D3 | 40.8 | 48 | 55.2 |  | x | x
D5 | Write documentation | D4 | 6.8 | 8 | 9.2 | x | x | x
D6 | Unit testing | D4 | 13.6 | 16 | 18.4 |  | x | x
D7 | System testing | D6 | 13.6 | 16 | 18.4 |  | x | x
D8 | Package deliverables | D5, D7 | 6.8 | 8 | 9.2 | x
E | Survey potential market | B, C | 20.4 | 24 | 27.6 |  |  |  | x | x
F | Develop pricing plan | D8, E | 10.2 | 12 | 13.8 |  |  |  | x | x
G | Develop implementation plan | A, D8 | 13.6 | 16 | 18.4 | x
H | Write client proposal | F, G | 6.8 | 8 | 9.2 | x

## Sheet3
Describe product | Develop marketing strategy | Design brochure | Develop product prototype | Requirements analysis | Software design | System design | Coding | Write documentation | Unit testing | System testing | Package deliverables | Survey potential market | Develop pricing plan | Develop implementation plan | Write client proposal